## Revision history
Revision history
Revision | Date | Desc | By
1.0 | 2014.05.09 | Initial document | Dungnv

## Project task
No. | Task | Progess (%)
| Overall | 55.29%
| Basic design | 100%
Functions
| Main screen | 100%
| PHP Frontent | 100%
| Resize panels | 100%
| Private content | 31.73%
| Create tree view | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Create grid view | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Create new folder | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Delete new folder | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Copy files, folders | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Move files, folders | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Paste files, folders | 100%
| Javascript | 100%
| PHP Frontent | 100%
| PHP API | 100%
| Share files, folders | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Upload files | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Download files | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Preview file | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Refresh | 93.33%
| Javascript | 80%
| PHP Frontent | 100%
| PHP API | 100%
| Login | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| User profile | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Show path on status bar | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Share content | 0%
| Create tree view | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Create grid view | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| View of share content (for unregisted users) | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Download files | 0%
| Javascript | 0%
| PHP Frontent | 0%
| PHP API | 0%
| Addon functions | 0%
| Right-click context menu | 0%
| Tree view | 0%
| Grid view | 0%
| Drag & drop (copy & move on Grid view) | 0%